## Sheet1
Edits are made in red "tracked changes".
Customer validation / good feedback
Specific targets for labelled data
Able to provide documentation
Deadline for amended workplan: 10 Sep 25 Deadline for sending inputs & new targets to UNICEF: 12 Sep 25
TEMPLATE 3 Tab 1: PROJECT DESIGN STATEMENT
BITZ IT CONSULTING LTD
Timeline |  | Tasks | Budget | Expected Changes/Targets | Signs of Success | What data will be generated during the project? | Key Personnel Responsible
|  | What are the major milestones you will achieve with the UNICEF Innovation Fund investment? Which activities do you need to do to achieve each milestone? Adjust the number of milestones and activities for each quarter as needed. |  | What will be different once the activity is done? (Provide specific numbers where possible.) | What will you measure/look at to assess if you completed the activity? And whether you achieved your desired outcome? Please specify the numeric values of your desired outcomes [ie.number of users]. Each activity must have at least one. | Each phase will generate some data. For example: (1) while you are developing a software solutions, there will be "commits" on GitHub; while you are developing new content, the volume of online data will increase. (2) while you are piloting a solution, you can track user numbers or user feedback; edits/updates to code or designs (3) while you are using a solution, you can track new users; deployment progress through an online tracker We require each phase to have real-time data that is accessible via Internet protocols linked to it. | Which team member is responsible for each task? Refer to the funding agreement for the definition of 'Key Personnel" and who can be included on this list.
Quarter 1 |  |  | $22 500,00
| Milestone 1 | Project Kick-off, Planning, and Research | $7 500,00
|  | Activity 1: Project Kickoff (Month 1) Objective: Establish the project framework and ensure alignment with stakeholders and objectives. Tasks: Define the project scope, objectives, and success metrics. Develop a governance structure and project management plan. Secure necessary funding, resources, and team members. Align project goals with UNICEF Ventures workshop objectives and other key stakeholders. |  | A detailed document outlining the project's scope, specific objectives, and measurable success criteria is developed and approved Stakeholders have a clear understanding of what the project aims to achieve and the metrics by which success will be measured A formal governance structure is established, including roles, responsibilities, and decision-making processes. A detailed project management plan is created The project has the necessary financial backing, tools, and human resources to move forward effectively The project's goals and deliverables are aligned with UNICEF Ventures Fund’s priorities and those of other critical stakeholders | Completed project scope document approved by all stakeholders. Agreed-upon objectives and success metrics documented and accessible to team members. Established governance structure with clear roles and responsibilities assigned. Secured funding and resources confirmed through signed agreements or contracts. | Project scope document, objectives and success metrics document, governance structure document, funding proposals and agreements. | Project Lead Key Stakeholders (e.g., funding partners, technical experts) Legal and Finance Teams
|  | Activity 2: Team Formation and Training (Month 1) Objective: Build and train a skilled team to execute project tasks effectively. Define the project scope, objectives, and success metrics. Develop a governance structure and project management plan. Secure necessary funding, resources, and team members. Align project goals with UNICEF Ventures workshop objectives and other key stakeholders. |  | A skilled, trained team onboarded, covering required domains. Privacy, security, and AI ethics training delivered to ensure compliance with UNICEF standards. Effective communication and collaboration structures established. | - Recruit and onboard team members with expertise in data science, AI, voice recognition, NLP, AI ethics, and child protection. - Provide training on privacy, security, and ethical considerations as required by UNICEF’s standards. - Establish clear communication protocols and collaboration tools. | - Recruited and onboarded relevant team members (data science, AI, voice recognition, child protection, etc.). - Conducted and documented training sessions on voice recognition, NLP, AI ethics, and child protection best practices. - Effective communication channels established, with confirmed team member understanding. | Project Lead, HR Team, Training Specialists
|  | Activity 3: Technical Infrastructure Setup (Month 2) Objective: Establish the technical infrastructure to support data processing and model training. Tasks: Plan and acquire necessary computing resources and storage capabilities. Set up infrastructure to support real-time voice recognition and translation services. Ensure compliance with security requirements for handling sensitive data. |  | Secured necessary computing resources: Acquired sufficient cloud computing capacity, storage space, and processing power to handle data analysis and model training. Acquired software licenses: Secured licenses for relevant software tools and platforms for data analysis, model development, and project management. Established secure and reliable data storage: Implemented secure data storage solutions with access controls and disaster recovery measures. | Secured computing resources agreements with cloud providers. Acquired and documented necessary software licenses if needed . Established and documented secure data storage procedures. | Infrastructure setup documentation, software license agreements, data storage configuration reports. | IT Lead System Administrator Security Specialists
| Milestone 2 | Validation and feedback activities to improve product and user experience(Month2) | $2 000,00
|  | Infrastructure Validation and Testing |  | Ensure that the technical infrastructure is fully functional, secure, and capable of supporting all data processing, model training, and testing needs. | - Conduct comprehensive infrastructure testing (compute resources, data storage, security protocols). - Verify the system's capacity to handle diverse data sources (voice, text). - Identify any bottlenecks in data flow and processing speed. - Ensure compliance with UNICEF security requirements for data handling. | - Fully functional technical infrastructure tested and validated. - Documented infrastructure testing results, including bottleneck resolutions. - Infrastructure complies with UNICEF security and privacy standards. | IT Lead, Infrastructure Team, Key Users
|  | Infrastructure Stress Testing (Month 2) |  | Test the capacity and reliability of the technical infrastructure under simulated loads. | - Simulate high traffic and data loads to test the infrastructure’s performance. - Measure response times, system stability, and resource utilization under load. - Identify areas for scaling and optimization. | - Successful completion of infrastructure stress tests. - Identified performance bottlenecks and optimization opportunities. - Infrastructure demonstrated ability to handle expected workloads. | IT Lead, System Administrator
|  | Security and Compliance Testing (Month 2) |  | Ensure that the infrastructure adheres to security protocols and compliance requirements. | - Conduct penetration testing and security audits to identify vulnerabilities. - Test data encryption and access control mechanisms. - Verify compliance with data protection standards (UNICEF and local regulations). | - Passed security and compliance tests. - Documented vulnerabilities addressed. - Infrastructure meets UNICEF and local security and privacy requirements. | Security Specialist, Legal Team, Data Protection Officer
|  | Data Processing and Integration Tests (Month 2) |  | Verify the infrastructure’s ability to support seamless data processing and integration for transcription, translation, and prediction tasks. | - Test integration of data processing components (voice recognition, NLP models). - Validate data flow between components and identify any latency or errors. - Ensure accurate data exchange and processing in real-time. | - Successful integration of data processing pipelines. - Verified real-time data exchange and processing. - Documentation of any identified issues and solutions. | Data Engineers, AI/NLP Specialists
| Milestone 3 | Privacy & Security Awareness(Month 2) | $1 000,00
|  | Data Privacy and Security Awareness Session |  | Improve understanding of data privacy and security issues | - Conduct sessions on privacy, security risks, and handling sensitive data. - Discuss masking and encryption strategies for voice recordings and PII. | - Improved privacy/security practices. - Team awareness of risks and mitigation strategies. | Privacy Officer, IT Security Specialist
|  | Privacy Impact Assessment (PIA) |  | Ensure compliance with privacy standards and mitigate risks | - Complete PIA for all data processing activities. - Assess risks and develop mitigation strategies. - Ensure alignment with data protection laws (e.g., GDPR). | - Completed PIA. - Documented mitigation strategies. - Compliance with privacy standards. | Privacy Officer, Compliance Manager
| Milestone 4: | Data Acquisition and Exploration (Months 2-3): | $4 000,00
|  | Formalize the process of data acquisition through MoUs with helplines and governments. Secure and prepare data for analysis and model training, ensuring ethical considerations and compliance. |  | - Task 1: Finalize MoU agreements with key data providers (e.g., helplines, government agencies) before starting data collection. - Task 2: Identify clear terms for data use, privacy, and ethical considerations with data partners. - Identify and secure data sources (e.g., calls, chats, reports, voice recordings). - Develop and document protocols for data cleaning, anonymization, and preparation. - Label data with relevant metadata (e.g., language, accent) to aid in training and evaluation. - Ensure alignment with UNICEF’s privacy, security, and data protection standards. | - MoUs secured with data providers to formalize ethical data access and partnerships. - Identified and secured diverse data sources: Secured access to calls, chats, reports, and voice recordings relevant to VAC/GBV cases, addressing ethical and privacy considerations. - Established data anonymization procedures: Implemented clear and consistent protocols for data anonymization to protect privacy and comply with regulations. - Completed initial data exploration: Analyzed data to understand content, distribution of variables, and potential challenges for further processing. | - Signed MoUs with data providers ensuring ethical data access and anonymization. - Documented anonymization procedures and implemented technical safeguards. - Completed initial data exploration reports summarizing key findings and potential challenges. | - Data Acquisition Lead - Data Scientists - Legal and Ethics Experts - Data Security Specialists
| Milestone 5 | Cohort Product Development
| Activity 1 | Attend technical product development session
| Activity 2 | Revision of the work plan at the end of the first quarter
| Milestone 6 | Capacity Building (Month 3) | $1 000,00
|  | - Conduct monthly workshops on advanced data preprocessing techniques for voice and text data (cleaning, normalization, labeling). - Provide training on privacy and security best practices, especially handling PII. - Hold capacity-building sessions on ML model development (transcription, translation, prediction). - Facilitate team discussions on ethical AI practices and responsible use of AI technologies. |  | - Improved technical capacity in data preprocessing, privacy/security, and AI/ML model development. - Increased awareness of ethical AI practices. | - Team members demonstrate advanced skills in data handling, security, and AI model building. - Improved accuracy and efficiency in project outcomes. - Consistent adherence to ethical standards. | - Training and workshop attendance records. - Documentation of improvements in data preprocessing, privacy, and AI modeling techniques. - Feedback from team members on knowledge gained. | - Project Lead - Training Specialists - Data Scientists - Privacy and Security Specialists - AI/ML Experts
| Milestone 7: | Data Privacy & Protection | $500,00
|  | Staff Policy against retaliation and ensure strict compliance |  | Staff Policy on handling client data and retaliation | Staff signing on the document |  | HR&Admin
|  | anonymizing sensitive information, and ensuring access control |  | Data Privacy policy | Successful implementation of Data Privacy and Confidentiality |  | Project Lead and System Architect
| Milestone 7: | Communications and Branding
|  | image + caption per month to be shared on your social media channels |  | Increased online presence and engagement. Reach a broader audience, raising awareness about the project. | Number of social media posts published; Engagement metrics (likes, shares, comments). | Social media analytics data; Post engagement metrics; Captions and images used. | Communications Officer, Social Media Manager
|  | blog post at the beginning of the quarter |  | Provide in-depth updates on project progress; Educate stakeholders and the public about key aspects of the project. | Number of blog posts published; Number of readers and reader engagement. | Blog post analytics (views, time spent on page); Reader feedback. | Content Writer, Communications Officer
| Milestone 8 | Voice Data Preprocessing and Transcription Pipeline(Month 3 -4) | $6 000,00 |  |  |  | Data Preprocessing Lead, NLP Experts
|  | Voice Data Collection & Preparation Voice Data Cleaning & Noise Reduction Build Initial Speech-to-Text Transcription Model Model Testing and Refinement Transcription Pipeline Documentation Generate Transcripts for NLP Tasks |  | Cleaned and preprocessed voice data - Developed initial transcription model Gather and organize voice data from identified sources, properly categorized and labeled. Reduce noise and normalize volume levels to improve transcription accuracy. Implement a speech-to-text model to transcribe voice data into text. Improve model accuracy through testing and refinement using multiple datasets. Document the transcription pipeline, including data cleaning and model setup. Run the transcription model on the full dataset to create transcripts for further NLP tasks. | Accurate transcription results: High-quality transcriptions were achieved on the test data, demonstrating the model's effectiveness. Robust data handling: Voice data was collected, categorized, and labeled systematically, ensuring a reliable dataset. Noise reduction and normalization: Preprocessing steps effectively reduced noise and normalized sound levels, improving transcription accuracy. Initial text generation: The model successfully generated transcribed text from the initial voice data samples. Enhanced accuracy: Through iterative refinement, the model's accuracy was significantly improved, as measured by the Word Error Rate (WER). Well-documented pipeline: The entire transcription process was documented comprehensively, facilitating reference and reproducibility. Complete transcript set: A full set of transcripts was created, ready for further analysis and a variety of NLP applications, such as case prediction and language translation. | Transcription Output & Preprocessing Reports Detailed reports on the transcription process and preprocessing steps, including any adjustments made. Voice Data Files Original voice data files used for transcription, such as call recordings or interviews. Cleaned Voice Data The voice data after undergoing preprocessing to remove noise and normalize sound levels, along with logs documenting the changes. Initial Transcription Samples Sample transcriptions generated during the initial stages of model development, used for preliminary performance evaluation. Performance Metrics Quantitative measures of the model's performance, including Word Error Rate (WER) and accuracy rate, obtained from model tests. Pipeline Documentation Comprehensive documentation of the entire transcription pipeline, making the process accessible and understandable to the team. Complete Transcribed Text Data The final, complete set of transcribed text data, ready for further analysis and NLP applications. | Data Preprocessing Lead Audio Engineers NLP Specialists AI/ML Engineers Data Scientists Project Manager Documentation Specialist
| Milestone 9: | Meeting Open Source Contractual Requirements(Month 2-3) | $500,00
|  | Review and understand open source and licensing requirements |  | Ensure a full understanding and compliance with open source and licensing requirements | All relevant compliance documents reviewed and understood. Compliance checklists completed. | Documentation of reviewed compliance documents in the project repository. | Legal Advisor, Open Source Compliance Officer
|  | Develop and implement a licensing strategy for open-source intellectual property |  | Develop a clear licensing strategy and apply an OSI-approved license to a public source code repository | Clear licensing strategy aligned with open source best practices. Public source code repository licensed under an OSI-approved license. | Licensing documentation; License applied in public repository. | Legal Advisor, Repository Manager
|  | Create a comprehensive project charter |  | Include vision statement, mission statement, community statement, licensing strategy, and identification of key trademarks | Clearly defined project goals, community guidelines, and licensing strategy. | Completed project charter document; Positive feedback from stakeholders. | Project Manager, Open Source Coordinator
|  | Develop detailed READMEs for all public repositories |  | Include an overview, developer setup instructions, repo connection to overall product, and list of Open Source software used | Clear and informative READMEs that guide developers and users. | Complete and well-structured READMEs in each public repository. | Technical Writer, Lead Developer
|  | Create and maintain comprehensive public Open Source documentation |  | Set up automated deployments of an HTML documentation site using CI/CD tools | Accessible and up-to-date documentation that reflects the latest codebase. | Automated documentation deployment; Accurate and updated documentation. | Documentation Specialist, DevOps Engineer
|  | Establish a quality assurance process for Open Source contributions |  | Implement unit testing frameworks for front-end/back-end, as applicable. Document user stories, test cases, and data structures | High-quality, reliable code contributions that meet established standards. | QA process documented and followed; Unit tests implemented and passing; Documented test cases and data structures. | QA Lead, Software Engineer
|  | Develop and enforce a Code of Conduct for all public Open Source repositories |  | Upload Code of Conduct to repositories and create internal procedures for handling reports | A safe and inclusive environment for all contributors and users. | Code of Conduct visible in all repositories; Established procedure for handling Code of Conduct reports. | Community Manager, Legal Advisor
|  | Implement and follow a structured Pull Request Workflow |  | Develop and enforce a workflow for managing code contributions through pull requests | Consistent and well-managed code contributions, fostering collaboration and code quality. | Pull Request Workflow documented; High engagement and contribution quality. | Repository Manager, Lead Developer
| Q1 Key Deliverables | Description
Front-end
| Project Scope Documentation | Clear definition of the project’s objectives, scope, and success criteria.
| User Interface Prototyping | Initial design and prototyping of the user interface, incorporating feedback from initial user testing sessions.
| Team Formation | Recruitment of team members with expertise in data science, AI, NLP, voice recognition, and child protection.
Backend
| Technical Infrastructure Setup | Deployment of cloud infrastructure, ensuring it supports data processing, voice recognition, and NLP model training.
| Data Acquisition Infrastructure | Setup of necessary infrastructure for data access, including data acquisition agreements with helplines/government agencies and anonymization procedures to ensure data security and privacy compliance.
| Voice Data Preprocessing Pipeline | Development of a pipeline for data cleaning, normalization, and noise reduction for voice data.
Quarter 2 |  |  | $26 000,00
| Milestone 1 | Text Data Preprocessing and Normalization(Month 4-5) | $10 000,00
|  | Clean and Preprocess Structured and Unstructured Text Data Clean text data by removing inconsistencies, duplicate entries, and irrelevant information. Preprocess for uniformity. |  | Cleaned text datasets ready for further analysis and NLP tasks. | Cleaned datasets; Logs of changes made to text data. | Cleaned structured and unstructured text files; Logs of changes. | Data Scientists, NLP Specialists
|  | Apply Text Normalization Techniques (e.g., spelling correction, stemming) Implement text normalization techniques to standardize data and improve consistency. |  | Text data with applied normalization techniques. | Normalized text datasets; Performance metrics for normalization techniques. | Normalized text datasets; Performance metrics. | NLP Specialists, Data Engineers
|  | Develop Reusable Text Processing Components for Future Pipelines Create modular components for reuse in future text-processing tasks. |  | ` | Codebase of reusable components; Documentation for integration. | Reusable text-processing functions and tools; Documentation. | NLP Specialists, AI/ML Engineers
|  | Document the Text Preprocessing Pipeline and Its Outputs Create comprehensive documentation for the text preprocessing pipeline, including steps and transformations performed. |  | Fully documented pipeline with easy-to-follow instructions. | Complete and clear documentation of preprocessing pipeline and outputs. | Documentation of preprocessing pipeline; Methodology, tools, and datasets. | Project Manager, Documentation Specialist
| Milestone 2: | Language Translation Pipeline(5-6) | $10 000,00
|  | Develop a Machine Translation Model for Structured and Unstructured Data Build an initial machine translation model capable of handling both structured (transcripts) and unstructured (raw) text data. |  | Completed machine translation model with testable outputs. | Model performance metrics (e.g., BLEU score); Source code and configuration files. | Machine translation model; Performance metrics; Model source code. | AI/ML Engineers, NLP Specialists
|  | Test Translation Accuracy Across Multiple Languages Conduct testing of the translation model across different languages, focusing on accuracy and fluency in translated text. |  | Performance evaluation on multiple languages. | Translation accuracy reports; Language-specific performance metrics. | Translated datasets; Accuracy reports. | AI/ML Engineers, Data Scientists
|  | Integrate Translation Module into the Transcription Pipeline Integrate the translation module within the voice transcription pipeline, allowing voice data to be translated into multiple languages. |  | Seamless integration of translation within the transcription pipeline. | Successful translation of voice data; Performance results documented. | Logs and outputs of translated voice data; Integration documentation. | System Engineers, Data Engineers
|  | Identify and Document Key Translation Challenges and Improvements Needed Analyze the translation model to identify challenges such as cultural nuances, language complexity, and technical limitations. Document areas for improvement. |  | Documented insights on key translation challenges and recommendations for improvement. | Report on translation challenges; Recommendations for model refinement. | Translation challenge reports; Improvement recommendations. | AI/ML Engineers, Documentation Specialist
| Milestone 4: | Validation and Feedback | $3 500,00
|  | User Testing (Product and UX) Conduct user testing sessions focusing on overall product functionality and user experience (UX). |  | Positive user feedback and identification of usability issues. | High task completion rate; Detailed feedback on usability. | User test scripts; Session recordings; UX evaluation reports. | Key Users
|  | User Testing (UI) Focus on testing the user interface (UI) for intuitiveness, aesthetics, and usability. |  | High ratings on UI design; Identification and resolution of UI issues. | Positive ratings on UI intuitiveness; Successful implementation of changes. | UI test scripts; UI design evaluation forms; Retest results. | Key Users
| Milestone 5: | Communications and Branding
|  | Social Media Presence Share 1 image + caption per month on social media channels. |  | Increased online presence and engagement. | Number of posts; Engagement metrics (likes, shares, comments). | Social media analytics data; Captions and images used. | Communications Officer, Social Media Manager
| Milestone 6: | Capacity Building | $1 500,00
|  | - Conduct monthly workshops on advanced data preprocessing techniques for voice and text data (cleaning, normalization, labeling). - Provide training on privacy and security best practices, especially handling PII. - Hold capacity-building sessions on ML model development (transcription, translation, prediction). - Facilitate team discussions on ethical AI practices and responsible use of AI technologies. |  | - Improved technical capacity in data preprocessing, privacy/security, and AI/ML model development. - Increased awareness of ethical AI practices. | - Team members demonstrate advanced skills in data handling, security, and AI model building. - Improved accuracy and efficiency in project outcomes. - Consistent adherence to ethical standards. | - Training and workshop attendance records. - Documentation of improvements in data preprocessing, privacy, and AI modeling techniques. - Feedback from team members on knowledge gained. | - Project Lead - Training Specialists - Data Scientists - Privacy and Security Specialists - AI/ML Experts
| Milestone 5 | Meeting Open Source Contractual Requirement | $500,00
| Activity 1 | MUST have a OSI-approved license distributed with public source code repositories by end of Q2.
| Activity 2 | Create contributing guidelines for all Open Source repositories. Explain how someone makes a contribution to the projects. Add to documentation website created in previous quarter.
| Activity 3 | Create public tickets/issues that correspond to planned features and known bugs/problems with Open Source repositories.
| Activity 4 | Use a public project management board to track progress on public tickets/issues (e.g. Taiga, GitHub/GitLab Projects, JIRA, Trello, or similar).
| Activity 5 | Add either developer or user documentation to the Open Source documentation site. (Hint: Developer docs often include API docs, architecture or system state diagrams, or deployment guides.)
| Activity 6 | Advance Open Source quality assurance. Target 15% code coverage for unit tests, if applicable.
| Milestone 7 | Privacy & Security - Development | $500,00
| Activity 1 | Develop documents and/or privacy agreements to include privacy-specific language in the Terms of Use, vendor contracts, user consent notice, and any other agreement that may be applicable.
| Activity 2 | Develop a privacy policy
| Activity 3 | Develop a data retention policy
| Milestone 8 | Cohort Product Development
| Activity 1 | Revision of the work plan at the end of the second quarter
| Q2 Key Deliverables | Description
Text Data Preprocessing and Normalization
| Clean and Preprocess Structured and Unstructured Text Data | Clean text data by removing inconsistencies, duplicate entries, and irrelevant information. Prepare data for further analysis and NLP tasks.
| Apply Text Normalization Techniques (e.g., spelling correction, stemming) | Implement normalization techniques to standardize data and improve consistency.
| Develop Reusable Text Processing Components for Future Pipelines | Create modular, reusable text-processing components for future tasks.
| Document the Text Preprocessing Pipeline and Its Outputs | Create comprehensive documentation for the text preprocessing pipeline, including steps and transformations.
Language Translation Pipeline
| Develop a Machine Translation Model for Structured and Unstructured Data | Build an initial machine translation model capable of handling both structured (transcripts) and unstructured (raw) text data.
| Test Translation Accuracy Across Multiple Languages | Conduct testing of the translation model across different languages, focusing on accuracy and fluency.
| Integrate Translation Module into the Transcription Pipeline | Integrate the translation module into the voice transcription pipeline for multilingual support.
| Identify and Document Key Translation Challenges and Improvements Needed | Analyze the translation model to identify challenges and document areas for improvement.
Validation and Feedback
| User Testing (Product and UX) | Conduct user testing sessions to evaluate overall product functionality and user experience (UX).
| User Testing (UI) | Test the user interface (UI) for intuitiveness, aesthetics, and usability.
Communications and Branding
| Social Media Presence | Share 1 image and caption per month on social media channels.
Capacity Building
| Conduct Monthly Workshops | Host workshops on advanced data preprocessing, privacy and security best practices, ML model development, and ethical AI practices.
Quarter 3 |  |  | $30 500,00
| Milestone 1 | Case Prediction Triage Model Development | $14 000,00 | Build the prediction model using preprocessed text and transcription data.Build the triage model using preprocessed text, transcription, and labeled datasets. (Includes speech-to-text, translation, entity extraction, classification, summarization) | Labeled datasets for prediction tasks (based on structured and unstructured text) Developed and tested a prediction model for case classification or event prediction Generated metrics for model performance (precision, recall, accuracy)Labeled datasets prepared for triage tasks (Swahili + English). - Use open-source datasets (FLORES, SMOL, Tatoeba, OpenSLR, Mozilla CV, FLEURS) plus helpline transcripts. - Embed human-in-the-loop corrections: counsellors validate auto transcripts, translations, and summaries during pilot. - Benchmark against baseline models (OPUS, NLLB-200, T5/MADLAD-400). | Iteratively improved the model based on feedback and real-world data |  | Evidence of completed deliverables / data | Verification by | Verified (Yes/No)
|  | Label Datasets for Case Prediction Tasks (100 hours) for Swahili. |  | Create and label datasets from preprocessed text and transcription data for case classification and triage tasks. | Datasets prepared with accurate labeling, structured for model input. | 100 hours of Labeled dataset, Labeled dataset documentation, quality checks, and dataset accessibility.Store final annotated dataset in repository with version control, plus quality control logs signed by reviewer. | Data Scientists, NLP Experts | We deployed our interface and progress is ongoing for labelling of the audio data, targeting 100 hours. Real time progress can be seen here: http://18.177.175.202:8010/dashboard
|  | Develop and Train the Prediction ,Translation,Quality Assurance,Named Entity Extraction,Classification,Summarization models |  | Build the initial model using labeled datasets, focused on Translation,NER, Classification and Summarization | Completed case prediction (Translation,Quality Assurance,Named Entity Extraction,Classification,Summarization) models ready for testing and refinement. | Model development logs, source code, and performance tests.,Keep Git commits, trained model checkpoint, and training configuration files. | AI/ML Engineers, Data Scientists | The Translation,Quality Assurance,Named Entity Extraction,Classification and Summarization models are done and next steps for next improvements are ongoing. All can be seen on Huggingface using this link: https://huggingface.co/openchs/models
|  | Test and Evaluate Model Performance (Precision, Recall, Accuracy, COMET)Test and Evaluate Model Performance (Precision, Recall, Accuracy, COMET, BLEU, ROUGE, and embedding-based scores such as LaBSE for translation and BLEURT/LLM-as-judge for summarization). |  | Run the prediction Case Triage models on test data to assess its performance, analyzing precision, recall, accuracy, and other key metrics. | Detailed performance metrics, highlighting strengths and weaknesses of the model. | Model performance reports, confusion matrices, and test dataset outputs.File final performance report signed off by project lead; attach confusion matrix screenshots. | AI/ML Engineers, Data Scientists | Detailed Performance have been provided in the AI Metrics.docx in the Sharepoint
|  | Iteratively Improve Model Based on Feedback and Real-World Data |  | Refine the prediction Case Triage models based on feedback from internal testing and real-world data, improving accuracy and robustness. | Improved prediction Case Triage Models(Translation,Quality Assurance,Named Entity Extraction,Classification,Summarization) model with higher performance metrics. | Iteration logs, updated model metrics, feedback reports, and improved datasets.Maintain iteration logbook, before/after metrics table, and feedback summaries as annex. | AI/ML Engineers, Data Scientists
| Milestone 2 | Integration and Optimization | $11 000,00 | Combine all pipelines (transcription, translation, and prediction) into a unified system. | End-to-end pipeline integrating voice transcription, language translation, and case prediction | Optimized model performance across different tasks Finalized reusable data cleaning code for voice and text data Fine-tuned model outputs to ensure reliability across all use cases
|  | Integrate the Transcription, Translation, and Case Prediction Triage Pipelines |  | Combine the individual models (transcription, translation, prediction Case Triage ) into a unified system. | A fully integrated system capable of processing input voice/text data through all pipelines. | Integration reports, updated architecture diagrams, and functional test logs. | System Architects, AI/ML Engineers | Fully Complete. The project team successfully integrated the individual AI components—speech-to-text transcription, multilingual translation, and case prediction triage—into a unified end-to-end service. The integrated pipeline is now capable of processing voice and text inputs seamlessly through all stages, producing transcription outputs, translated content, and automated case triage predictions within a single workflow. This integration has been implemented directly within the helpline case management process, enabling AI-assisted triage to function as part of the operational case workflow. Functional integration testing has been completed, confirming that the service runs reliably end-to-end.
|  | Ensure Seamless Data Flow Between the Modules |  | Optimize data flow across transcription, translation, and case prediction pipelines, ensuring smooth handoffs. | Data flows seamlessly between the different modules with no loss of information or bottlenecks. | Data flow diagrams, latency reports, logs of data passed between modules. | System Architects, Data Engineers
|  | Test the Integrated System End-to-End and Identify Performance Bottlenecks |  | Perform full system testing to ensure the integrated pipeline works without errors, identifying any potential bottlenecks. | Successful end-to-end tests with performance bottlenecks identified and documented. | System performance reports, test logs, identified bottleneck locations. | AI/ML Engineers, QA Specialists
|  | Finalize Integration Documentation and Prepare for Deployment |  | Complete documentation of the integrated system, covering all modules, and prepare the system for deployment. | Ready-to-deploy system with comprehensive integration documentation. | Final system documentation, deployment plans, user guides. | Technical Writers, System Architects | Fully Complete. The project team finalized comprehensive documentation for the fully integrated AI system, covering all core modules including transcription, translation, and case prediction triage. Deployment readiness materials were completed, including system architecture documentation, integration specifications, operational workflows, and deployment guidance. User-facing documentation and technical handover materials were also prepared to support implementation within the helpline environment. The system is now ready for deployment, with complete supporting documentation and deployment plans available for verification.
| Milestone 3 | User Pilot Testing | $5 000,00
|  | Validation and Feedback: Validate the integrated system, focusing on the performance of case prediction, transcription, and translation, NER, Classification , QA and Summarization. |  | System Validation: Ensure the integrated pipelines (case triage, transcription, and translation) are functioning seamlessly together with high accuracy and user satisfaction in real-world scenarios. | "High accuracy of the case triage model; Smooth integration of transcription, translation, and prediction with no bottlenecks or data loss." | "Performance reports on accuracy, latency, and data flow; User feedback on system usability; Model accuracy and workflow efficiency reports." | "QA Specialists, Data Scientists, Key Users"
|  | Validate the performance of the integrated system in real-world scenarios, ensuring that data flows seamlessly between all pipelines. |  | Effective System Integration: Ensure data processing flows smoothly across transcription, translation, and Case Triage pipelines with high accuracy and no latency or data loss. | "Successful end-to-end testing with no errors in data flow; Case Triage accuracy meets or exceeds target performance metrics (precision, recall, etc.)." | "Test logs, performance reports, and feedback on data processing efficiency and accuracy; Documentation on issues identified and resolved during testing." | "System Architects, AI/ML Engineers"
|  | Conduct pilot testing of the model within the helpline with controlled user groups (Month 9). Evaluate model effectiveness and user experience in a real-world setting. |  | Improved Model Accuracy: Refine the prediction model based on user feedback, ensuring it accurately classifies cases and events such as VAC/GBV, Categories, Priority. | "User feedback shows satisfaction with the case triage accuracy; Identified areas for improvement incorporated into model refinement." | "User feedback forms, model iteration logs, updated performance metrics, and reports on user satisfaction with case predictions." | "AI/ML Engineers, UX Researchers, Key Users"
|  | Validate UI/UX of the integrated system to ensure a user-friendly and intuitive interface for real-world application. |  | Enhanced User Experience: Ensure the integrated system's interface is intuitive, easy to navigate, and accessible, based on user feedback and iterative improvements. | "Positive feedback on UI/UX design, showing ease of use and improved user interaction; Iterative UI/UX enhancements based on usability testing results." | "User feedback on UI/UX, usability test reports, design iteration logs." | "UX Researchers, Product Designers, Key Users"
|  | Conduct final rounds of fine-tuning based on pilot testing results and any additional data collected during real-world usage. This includes optimizing models to address any limitations or issues observed during the pilot phase. |  | Models optimized to address issues from pilot testing. Improved accuracy and usability based on real-world data. | Documentation of changes made. Improved model performance metrics. Positive feedback from real-world usage. | Updated model performance reports. Real-world usage data. Feedback from pilot testing and real-world applications | AI/ML Engineers, Data Scientist, Project Manager
| Milestone 4 | Communications and Branding
|  | image + caption per month to be shared on your social media channels |  | Increased online presence and engagement. Reach a broader audience, raising awareness about the project. | Number of social media posts published; Engagement metrics (likes, shares, comments). | Social media analytics data; Post engagement metrics; Captions and images used. | Communications Officer, Social Media Manager
|  | blog post at the beginning of the quarter |  | Provide in-depth updates on project progress; Educate stakeholders and the public about key aspects of the project. | Number of blog posts published; Number of readers and reader engagement. | Blog post analytics (views, time spent on page); Reader feedback. | Content Writer, Communications Officer
| Milestone 5: | Capacity Building | $0,00
|  | - Conduct monthly workshops on advanced data preprocessing techniques for voice and text data (cleaning, normalization, labeling). - Provide training on privacy and security best practices, especially handling PII. - Hold capacity-building sessions on ML model development (transcription, translation, prediction). - Facilitate team discussions on ethical AI practices and responsible use of AI technologies. |  | - Improved technical capacity in data preprocessing, privacy/security, and AI/ML model development. - Increased awareness of ethical AI practices. | - Team members demonstrate advanced skills in data handling, security, and AI model building. - Improved accuracy and efficiency in project outcomes. - Consistent adherence to ethical standards. | - Training and workshop attendance records. - Documentation of improvements in data preprocessing, privacy, and AI modeling techniques. - Feedback from team members on knowledge gained. | - Project Lead - Training Specialists - Data Scientists - Privacy and Security Specialists - AI/ML Experts
| Milestone 6 | Meeting Open Source Contractual Requirement | $500,00
| Activity 1 | Advance Open Source quality assurance. Set up a Continuous Integration / Continuous Deployment (CI/CD) pipeline from source code repository. Set up checks or tests on new Pull Requests. Target 40% code coverage, if applicable. | [5 empty] | See https://unicef.sharepoint.com/:w:/r/teams/OOI-Venture/Ventures%20Shared%20Folder/Venture%20Fund/Startup%20Portfolio%20Management/Heath%20Systems%20Strengthening%20Cohort%20(2023-24)/Company%20Folders/BITZ%20IT/Workplan/Open%20Source%20Contractual%20Obligations%20Checklist%20(BITZ).docx?d=wb57213fe77b3496d96c631ffad7beabd&csf=1&web=1&e=HIO0yJ
| Activity 2 | Add ticket/issue templates to source code repositories for new tickets opened by the public and the core contributor team.
| Activity 3 | Create "Good First Issues" for bite-sized, low-commitment contributions for new developers to make to your source code repositories.
| Activity 4 | Add either developer or user documentation to the Open Source documentation site, whichever was not completed the previous quarter.
| Activity 5 | Review compliance against DPG criteria and address any gaps
| Milestone 7 | Privacy & Security - Development and refinement of policies
| Activity 1 | Develop documents and/or privacy agreements to include privacy-specific language in the Terms of Use, vendor contracts, user consent notice, and any other agreement that may be applicable.
| Activity 2 | Develop a privacy policy
| Activity 3 | Develop a data retention policy
| Milestone 8 | Cohort Product Development
| Activity 1 | Revision of the work plan at the end of the third quarter
Q3 Key Deliverables
Case Prediction Model Development
| Labeled Datasets for Case Prediction Tasks | Datasets prepared with accurate labeling, structured for model input.
| Prediction Model | Completed case prediction model ready for testing and refinement.
| Model Performance Metrics | Detailed performance metrics including precision, recall, accuracy.
| Improved Prediction Model | Iteratively refined prediction model with higher performance metrics.
Integration and Optimization
| Integrated System | Fully integrated system combining transcription, translation, and prediction pipelines.
| Seamless Data Flow | Ensured smooth data flow between different modules with no bottlenecks.
| End-to-End System Test | Successful testing of the integrated system with identified performance bottlenecks.
| Final Integration Documentation | Comprehensive documentation of the integrated system, ready for deployment.
Validation and Feedback
| System Validation | Ensured high accuracy and seamless functionality of the integrated system in real-world scenarios.
| Data Flow Validation | Confirmed effective data processing across all pipelines with no latency or data loss.
| Prediction Model Feedback | Refined model based on user feedback for accurate case and event classification.
| UI/UX Validation | Improved user experience of the integrated system’s interface based on user feedback.
Communications and Branding
| Social Media Engagement | Shared images and captions to increase online presence and engagement.
| Blog Post | Published a blog post to update stakeholders and the public on project progress.
Capacity Building
| Workshops and Training | Conducted workshops and training sessions on data preprocessing, privacy/security, ML model development, and ethical AI practices.
Quarter 4 |  |  | $17 500,00
| Milestone 1: | AI Model Deployment and Performance Evaluation | $9 000,00
|  | Deploy the model with partner. Run walkthrough and training sessions with call operators and their supervisors to prepare for their onboarding. Develop a FAQ for call operators to self-help. Document the workflow enhancements for the child helpline over a period of 1 month. Evaluate the Full-Scale Deployment of the Model: Analyze the performance of speech to text/transcription model's effectiveness in child helplines, specifically in identifying VAC/GBV cases during calls. Evaluate AI's role in reducing response times and improving intervention outcomes. Identify whether AI can help recognize prank or blank cases before calls end and compare AI-assisted interventions against traditional methods (A/B testing). |  | Improved Case Identification classification: Use AI to address human limitations in identifying VAC/GBV cases during calls. Target: AI helps identify cases before the call ends. Faster Response Times: AI automates case triage, reducing delays in response. Current response times are [8-10 minutes] minutes, and target is to reduce this by [50%/ 5 minutes]. Enhanced Support: AI allocates resources and provides recommendations. Target: Iimproved case classification. Operators and supervisors fully onboarded; FAQ supports self-help; workflows become more efficient; transcription accurately identifies VAC/GBV cases; AI reduces response times; prank/blank calls detected early; AI-assisted workflow outperforms traditional methods | Case identification classification accuracy improved through NLP and machine learning, reduced response times through AI-enabled automation, and enhanced support evidenced by improved intervention outcomes referalls such as arrests or injuries avoided. A/B test provides empirical evidence for AI effectiveness. Partner confirms deployment; operators trained and using system; FAQ published; workflow improvements measurable; ASR performance within target; response times reduced; A/B test shows AI advantages | Quantifiable metrics: case identification accuracy rates, response time reductions, intervention outcome improvements. A/B testing results compare AI-assisted system with the traditional process. Training attendance sheets; walkthrough logs; system access logs; FAQ document; workflow maps; efficiency metrics; transcribed call samples; error logs; call handling times; A/B test records; KPI measurements | Data Scientist, Child Protection Specialist, Evaluation Officer, AI/ML Engineers | Deploy the model with partner → Deployment documentation with system architecture diagrams, API endpoints, and signed partner acceptance form. Run walkthrough and training sessions with call operators and supervisors → Training attendance sheets with signatures, session recordings/slides, and pre/post-training assessment scores. Develop FAQ for call operators → Published FAQ document (PDF/web link) with minimum 20 common scenarios and troubleshooting steps. Document workflow enhancements over 1 month → Workflow comparison report showing before/after process maps with efficiency metrics. Analyze performance of speech to text/transcription → ASR performance evaluation report with WER, CER across 30-50 manually transcribed call samples, including error analysis by language/accent. Evaluate AI's role in reducing response times → Statistical analysis report comparing average call handling times (baseline vs AI-assisted) with sample size n≥200 calls. Compare AI-assisted vs traditional methods (A/B testing) → A/B test results report with statistical significance tests (p-values), sample sizes for both groups, and key performance indicators comparison table. *** Signed deployment acceptance; training attendance sheets; session recordings; published FAQ; workflow improvement report; ASR performance report; statistical analysis report; A/B testing results with KPIs and p-values
| Milestone 2: | Survey and Project Findings Dissemination | $2 000,00
|  | Design a survey or focus group or in-depth interview questionnaire with call operators at a child helpline and seek inputs from Evidence of Impact mentor and PM before disseminating and implementing the questionnaire. Discuss both internally and with mentors and PM which subjects to cover. Prepare and Disseminate Project Findings: Develop reports, publications, and conference presentations to share findings. Engage stakeholders to refine the model and promote broader adoption. Present model benefits and adoption to child helplines and related organizations, aiming for replication in at least three systems. Fine-Tuning of the model is done on an ongoing basis and BITZ will report any improvements during the Graduation Roundtable and various reporting platforms e.g. Final narrative report. If usability and UX evaluation remains important topics, BITZ may include the activities below: AI System Usability Evaluation User Testing (Product and UX): Conduct user testing to evaluate product functionality and user experience, collecting feedback from 20 users. Implement changes based on feedback. Run A/B testing to compare the AI-assisted system with the current process for key metrics like case identification accuracy, response times, and victim satisfaction. User Interface Improvement User Testing (UI): Conduct user interface testing to ensure UI is intuitive, collecting feedback f rom 50-100 users. 20 users |  | Increased Awareness of the Models: Targeted outreach to child protection organizations for broader recognition and integration. Adoption of the Model: At least one child helplines to adopt the model. Contribution to Field Knowledge: Share insights on AI applications in child protection. Stakeholder Engagement: Incorporate feedback from child protection specialists to refine the model. Impact: Track improvements in case identification and response times to measure the impact on child safety. Enhanced Product Functionality: Gather feedback and make improvements to the product's functionality and UX. Measure effectiveness through controlled experiments (A/B testing) comparing AI vs. non-AI workflows. Improved UI: Based on user feedback, enhance the intuitiveness and usability of the UI. Measure impact through usability metrics and user satisfaction rates post-improvement. Validated questionnaire ready for data collection; project findings widely shared; model adoption promoted; replication achieved in 1 systems | Published reports, articles, and presentations with positive stakeholder feedback. At least three one child helpline systems adopting the model, improving case identification, response times, and intervention outcomes. Actionable feedback from users, leading to tangible improvements in product performance and satisfaction. Positive A/B testing results show improvement in case handling. Positive user feedback and measurable improvements in UI intuitiveness and usability post-changes. Questionnaire approved by mentor/PM; survey/focus group conducted; reports, publications, and presentations completed; stakeholders engaged and adoption initiated | Dissemination materials, adoption metrics (e.g., new helpline systems), stakeholder feedback, performance metrics on AI effectiveness in case identification and response times. User feedback forms, usability metrics, A/B testing results comparing AI and non-AI workflows, and lists of issues with actions taken to improve UX and functionality. UI feedback reports, design iteration logs, usability metrics, and satisfaction rates. Completed questionnaires; focus group transcripts; interview notes; reports; conference presentation materials; stakeholder feedback | Communications Lead, Research Analyst, Stakeholder Engagement Coordinator UX Researcher, AI/ML Engineers UX Researcher, Design Lead | Design survey/focus group/interview questionnaire with call operators → Final questionnaire document (PDF) with minimum 15 questions covering usability, workflow impact, and satisfaction metrics, including both quantitative (Likert scale) and qualitative questions. Seek inputs from Evidence of Impact mentor and PM before disseminating → Email thread or meeting minutes showing mentor/PM feedback with tracked changes document demonstrating incorporation of their suggestions into revised questionnaire. Discuss internally and with mentors which subjects to cover → Meeting minutes from internal team discussion and mentor consultation listing agreed-upon survey themes (e.g., usability, accuracy perception, workload impact, training adequacy). Finalized questionnaire; survey/focus group/interview datasets; published reports; conference presentation slides; adoption confirmation in target systems
| Milestone 3: | Data labelling | $1 500,00 |  |  |  |  | Prepare and Disseminate Project Findings → Published deliverables package including: technical report (PDF), 2-page policy brief for non-technical audiences, and presentation deck submitted to at least one conference or stakeholder forum. Engage stakeholders to refine model and promote broader adoption → Stakeholder workshop report documenting feedback from a child helpline organization, with action items for model improvements and adoption roadmap. Present model benefits aiming for replication in at least 3 systems → Presentation materials delivered to target organizations + signed Letters of Intent or MoUs from at least 3 child helpline systems expressing interest in adopting/piloting the OpenCHS model
|  | Label additional 50h of helpline data with the support of call centre operators by 31 Jan 26. BITZ may explore for secondments from the call centres and renumerate the call operators during the period Identify ways to capture the feedback from the case workers on the speech to text / quality of transcription e.g. Thumbs-up or down buttons and feedback box in the system |  | High-quality annotated dataset for model training; operators engaged and motivated; systematic collection of feedback on transcription quality | 50h of calls labeled; secondments completed; feedback collected from operators via the system | Labeled audio files; operator participation logs; feedback entries from thumbs-up/down and text boxes |  | Label additional 100h of helpline data with call operator support → Annotation completion report from Label Studio showing:- Total hours labeled (target: 100h) - Inter-annotator agreement scores (IAA/Kappa) - Number of contributing annotators Note: The link (http://18.177.175.202:8010/dashboard) is live evidence. Identify ways to capture caseworker feedback on transcription quality → Feedback mechanism design document detailing: - UI mockups or screenshots of thumbs-up/down buttons placement - Feedback form fields specification (rating scale, comment box, error categorization) - Data schema for storing feedback (what gets captured: timestamp, user ID, call ID, rating, comments) - Implementation plan or integrated feature in the OpenCHS interface. Annotated dataset; operator attendance/secondment logs; system feedback logs
| Milestone 4: | Publication of synthetic data | $500,00
| Milestone 5: | Communications and Branding
|  | Communications and Branding: Share one image + caption per month on social media to raise awareness and engagement with the project. |  | Increased Online Presence: Increased awareness through social media engagement. Targeting increased recognition of the project among child protection stakeholders and a wider audience. | Number of social media posts published and engagement metrics (likes, shares, comments). | Social media analytics data showing engagement rates, reach, and audience demographics. | Communications Officer, Social Media Manager
|  | Blog Post: Publish a blog post to provide in-depth updates on project progress and educate stakeholders on the project. |  | Stakeholder Engagement: Inform stakeholders about key developments in the project, with a focus on AI outcomes in child protection. | Number of blog posts published and reader engagement metrics (views, time spent on page, feedback). | Blog post analytics (views, time spent on page), reader feedback on content. | Content Writer, Communications Officer
| Milestone 6 | Documentation & QA Compliance | $2 000,00
|  | Open Source Documentation: Finalize comprehensive user and developer documentation, ensuring open-source compliance. |  | Comprehensive Documentation: Ensure detailed, user-friendly documentation for developers and end-users. Include guidelines for data privacy and security practices, especially related to handling sensitive PII. | Comprehensive documentation for users and developers with clear guidelines on privacy and security. Achieve at least 80% code test coverage and positive user feedback on documentation clarity. | Documentation logs, user feedback on documentation, and statistics on document downloads or views. | Documentation Lead, Privacy Officer
| Milestone 7 | Code Testing & Privacy Audits | $1 500,00
|  | Open Source Quality Assurance: Achieve at least 80% code test coverage and ensure privacy compliance. |  | Improved Code Quality and Privacy Compliance: Achieve 80% test coverage and ensure that the model and system meet privacy and data protection requirements for sensitive data (PII). Address Q4 security and privacy feedback regarding data handling. | Test coverage reports showing at least 80% coverage, positive privacy and security audits, and compliance with data protection regulations. | Code coverage metrics, security and privacy audit reports, and number of tests run. | QA Lead, AI/ML Engineers, Privacy Officer
Milestone 9:
Data Scientist, Privacy Officer
| Milestone 8 | Meeting Open Source Contractual Requirement
Finalize Open Source Documentation
Finalize Open Source Quality Assurance
Growth Planning, Contextual Analysis, and Focused Support with Open Source Mentor
| Milestone 9: | Cohort Product Development
| Activity 1 | Attend virtual graduation
| Activity 2 | Initiate submmission for the DPGA for consideration
| Activity 3 | Work with your privacy and security mentor to ensure you meet the requirements
of DPG indicator 7 and 9a.
| Milestone 10 | Data Privacy Strategy Development and Data processing strategy development | $1 000,00
|  | Data Processing Strategy Development: Review the data schema to ensure data processing accuracy and compliance with privacy laws. Develop a data map for short-term (one year) forward strategy. Ensure sensitive PII remains protected in compliance with local and international privacy laws. Review your data schema to ensure data processing practices are accurate/updated |  | Accurate Data Processing: Implement a robust data processing strategy that aligns with privacy regulations, focusing on secure handling of sensitive PII. Compliance with Privacy Laws: Ensure PII is not misused or leaked, incorporating Q4 feedback on government misuse and data leakage prevention. Outcome: Data schema and strategy meet privacy laws, ensuring trust among stakeholders. Data schema reviewed and updated; data map finalized; privacy compliance verified | Data map documenting data processing practices, privacy audit reports, and compliance with international and local privacy regulations. Updated data schema; data map document; compliance checklist; PII protection logs | Data Scientist, Privacy Officer |  | Review data schema to ensure data processing accuracy and compliance with privacy laws → Data schema documentation (ERD diagrams + data dictionary) with compliance mapping table showing how each data field aligns with GDPR Article 6 lawful basis, and UNICEF data protection standards, including data retention periods per field. Develop a data map for short-term (one year) forward strategy → Data flow diagram showing: - Data lifecycle: collection → processing → storage → access → deletion - Systems/tools at each stage (Label Studio, MLflow, production database, etc.) - Data volume projections (audio hours, transcriptions, user records) - Quarterly milestones for data activities over 12 months - Risk assessment for each data processing stage. Ensure sensitive PII remains protected in compliance with privacy laws → PII protection implementation report documenting: - Anonymization/pseudonymization techniques applied to caller data - Access control matrix (who can access what data, role-based permissions) - Encryption methods (in-transit: TLS/SSL, at-rest: AES-256) - Data Processing Agreement (DPA) signed with UNICEF and partner child helplines - Consent management process for audio recording/transcription. Approved data processing strategy document; updated schema and data map; internal privacy audit report
Determine whether the current data processing strategy is appropriate (given privacy & data protection considerations) and develop a data map of the data processing strategy to be in the short term (one-year forward).
Q4 Key Deliverables
| Model Validation and User Testing | Description |  | Technical Development
| Model Validation and User Testing |  |  | Model deployment and performance evaluation
| Improved Case Identification | Validate model outputs through feedback, improve usability, and facilitate user testing sessions. Collect feedback, refine models, and summarize user insights. |  | Onboarding of operators and supervisors
| Completion of User Testing Sessions | Increased accuracy and speed in identifying VAC/GBV cases, with improved response times and support outcomes. |  | Labelling of helpline data (100h)
| Model Evaluation and Dissemination | Completion of 30+ user testing sessions with feedback on model performance, accuracy, speed, and usability. |  | Publication of synthetic data (generated from real helpline data)
| Increased Adoption | Evaluate the model’s deployment within child helplines, assessing its impact on VAC/GBV case identification and response times.
| Communications and Branding | Adoption of the model by at least three new child helpline systems and increased awareness of its effectiveness.
Social Media Engagement
| Blog Post | Share images and captions monthly to increase online presence and engagement.
| Data Processing Strategy Development | Publish a blog post at the beginning of the quarter to update stakeholders and the public on project progress.
Review Data Schema
| Data Processing Strategy | Review and update the data schema to ensure accurate and current data processing practices.
| Cohort Product Development | Develop a data map and strategy for processing, ensuring it aligns with privacy and data protection considerations for the upcoming year.
Virtual Graduation
| DPGA Submission | Attend the virtual graduation event.
| Privacy and Security Compliance | Initiate submission for the DPGA for consideration.
Work with the privacy and security mentor to meet DPG indicator 7 and 9a requirements.
Total Budget
List all new product features that will be developed in the one-year investment period
Voice & Text: Capture and understand helpline calls in different languages.
AI Case Triage: Use voice, text, and AI to Assist Agents in Classifying cases potential VAC/GBV cases.
Helpline Staff Dashboards: Show case details, predictions, and insights to staff.
Reports & Analysis: Track AI performance and child safety outcomes. Publication of synthetic data (generated from helpline data)
Please list all Open Source components generated through the workplan
All of the above will be open source
Please list any proprietary components developed though the workplan
All new products will be open source
| Revised workplan | Original workplan | Difference | Disbursement amount | Status
Q1 | $22 500,00 | $22 500,00 | $- | $22 500,00 | Disbursed
Q2+3 | $56 500,00 | $55 000,00 | $1 500,00 | $55 000,00 | Disbursed
Q4 | $17 500,00 | $22 000,00 | -$4 500,00 | $19 000,00
Total | $96 500,00 | $99 500,00 | $(3 000,00) | $96 500,00
Q4 disbursement amount | $41 500,00